## Sheet1
Task | Start Date | End Date | Status | Responsible
Kick off meeting with team members | 25/09/2025 |  | Done
Electrical parts picking | 2025-06-10 | 20/10/2025 | In Progress | Julien, Zakaria
Rules summery | 25/09/2025 | 29/09/2025 | Done | Team Members
Mechanical approach | 29/09/2025 | 18/11/2025 | In Progress | Adeel, Melchior
Fork the main repo | 29/09/2025 | 2025-06-10 | Done | Julien
Gazebo simulation | 17/10/2025 |  | To Do | Zakaria
Localization system | 29/09/2025 | 25/12/2025 | In Progress | Karam
Evalutae Mechanical desgin | 17/10/2025 | 31/10/2025 | In Progress | Team Members
Implimenting the Algorithm | 17/10/2025 | 22/10/2025 | In Progress | Karam
System engeneering | 22/10/2025 | 31/10/2025 | In Progress | Karam
BOM (bill of material) |  |  | To Do | Zakaria, Julien